## CS1K Installer's Roadmap
Table of contents
Click on a link below to go to that sheet.
| Contact information and signatures | Installation | Post-Installation
|  | Remote access | Post check
| Pre-Installation | Example Timelines
| CS 1000 prerequisites | Gotchas
| System + Site Requirements | Vintage Requirements
| Power & Grounding | Upgrade Procedure R6
| Cabinet installation | Upgrade Procedure R7
| Cabling installation | Upgrade Procedure R 7.5
| System operation | UCM Security issues
| System software | High Scalability
| VoIP Networking Parameters | Geographic Redundancy
| Product Bulletins | FAX issues with VOIP - MGC's
Communications Server 1000 Installation and Upgrade Checklist
This Avaya Communications Server 1000 Installation and Upgrade Checklist is an aid to assist during installations or upgrades of CS 1000 systems. While all possible attempts are made to ensure its accuracy, it is not intended to be the definitive source regarding such topics. The definitive source for information is the Product Specific Documentation, Product Bulletins, and General Release Bulletins. In cases of discrepancy, the Product Specific Documentation, Product Bulletins, or General Release Bulletins are deemed to be correct.
(Avaya Document Number: 18-604033
September 2011 01.00 (Standard)

## Contact information
◄ Back to table of contents
Contact information and signatures
Make a copy of the checklists in this document and return the originals to the RACS Engineer assigned.
Review all reference material and documentation for Communications Server 1000 Release 6.0/7.X prior to installation.
| Reference documentation for Communications Server 1000 6.0 and 7.X can be found at |  | http://support.avaya.com
Note: Some of the preparation steps in this document require that you have access to system passwords. Take appropriate steps to guarantee the
security of your passwords.
Contact information
|  | Project # / Contract # : |  | Requested install date:
|  | Site Address: |  | Date of pre-site:
|  | Project Manager/Leader: |  | Purchase order # :
Completed by home office
Site ID # :
Clarify ticket # (if applicable):
|  | Installer: |  | Phone # :
|  | Installation coordinator: |  | Phone # :
Customer
Name:
Contact:
E-mail address:
|  | Customer address: |  | Phone # :
|  | Address line 2: |  | FAX # :
City:
State:
Zip code:
LAN administrator
|  | Name: |  | Phone # :
|  | E-mail address: |  | FAX # :
Switch technician
|  | Name: |  | Phone # :
|  | E-mail address: |  | FAX # :
Distributor
|  | Name: |  | Phone # :
|  | Contact: |  | FAX # :
E-mail address:
Signatures ( as required)
|  | Dist./Sales contact: |  | Date:
|  | Customer contact: |  | Date:

## CS 1000 prerequisites
◄ Back to table of contents
CS 1000 prerequisites
This Avaya Communications Server 1000 Installation and Upgrade Checklist is an aid to assist during
installations or upgrades of CS 1000 systems. While all possible attempts are made to ensure its accuracy, it
is not intended to be the definitive source regarding such topics. The definitive source for information is the
Product Specific Documentation, Product Bulletins, and General Release Bulletins. In cases of discrepancy,
the Product Specific Documentation, Product Bulletins, or General Release Bulletins are deemed to be correct.
Complete this checklist to ensure that switch prerequisites for Communications Server 1000 are met.
Check the items in the checklist to confirm that they have been completed. Provide additional information where requested.
This checklist is to be completed and verified during coordination conference calls.
The Installation Coordinator is responsible for forwarding copies of this document to parties involved with installation.
The responsibilities for completing this checklist are as follows:
| Checklist section | To be completed by Distributor (Switch Tech) | To be completed by Customer
Communications Server 1000 readiness
Contact Center readiness
CallPilot readiness
Telephony Manager readiness
CS 1000 readiness (one week prior to work window) | [5 empty] | Date of availability
| Customer Advisement |  |  |  | Date:
The Communications Server 1000 and related systems (such as CallPilot and Contact Center)
should be locked down. No MAC work should be done until the upgrade has been
completed. Any emergency changes should be entered into a sequential log. The
end customer should be made to understand that undocumented changes may be
lost in the event backup databases are required during the work window.
What is the configuration of the voice switch (PBX) being used?
| Option 11C Cabinet Automatic conversion is supported directly from an Option 11C Cabinet Releases: 23, 24, 25, 2.0, 3.0,4.0, 4.5, 5.0, 5.5, 6.0, and 7.0. Given Option 11C Cabinet is not available in Release 7.5 it must be converted to a CS1000E system. The conversion will require an upgrade to a CPPM, CPDC processor and MGC, or CPMG as the SSC processors are not supported on IP capable systems. |  |  | Type of system:
Option 11C Chassis Automatic conversion is supported directly from an Option 11C Chassis Releases: 23, 24, 25, 2.0, 3.0,4.0, 4.5, 5.0, 5.5, 6.0 and 7.0. Given Option 11C Chassis is not available in Release 7.5, it must be converted to a CS1000E system. Conversion will require an upgrade to a CPPM, CPDC processor and MGC, or CPMG as the SSC processors are not supported on IP capable systems.
| Communication Server 1000M Chassis/Cabinet Conversion to Communication Server 1000 Release 7.0 is only supported if the Call Processor is updated to CPPM and CPDC. Automatic conversion is supported directly to Communication Server 1000E Chassis/Cabinet Release 7.5 from release 3.0, 4.0 4.5, 5.0, 5.5, 6.0 and 7.0. |  |  | S/W Release:
| Communication Server 1000S Conversion to Communication Server 1000 Release 7.5 is only supported if the Call Processor is updated to CPPM, CPDC, or CPMG. When updating the processor the system will become a CS1000E. Automatic conversion is supported directly to Communication Server 1000E Release 7.0 from release 1.0, 1.1, 2.0, 3.0, 4.0, 4.5, 5.0, 5.5, 6.0 and 7.0. |  |  | SN:
Communication Server 1000M Single Group/Multi Group Conversion to Communication Server 1000 Release 7.5 is supported with large system platforms equipped with Pentium based processors only (Intel Pentium IV). Automatic conversion is supported directly to Communication Server 1000M Release 7.5 from release 3.0, 4.0, 4.5, 5.0, 5.5, 6.0 and 7.0.
Communication 1000E Automatic conversion is supported directly to Communication Server 1000E Release 7.5 from release 4.0, 4.5, 5.0, 5.5, 6.0 and 7.0.
Option 61C, 81C Conversion to Communication Server 1000 Release 7.5 is supported with large system platforms equipped with Pentium based processors only (Intel Pentium IV). Automatic conversion is supported directly to Communication Server 1000M Release 7.5 from release 23, 24, 25, 2.0, 3.0, 4.0, 4.5, 5.0, 5.5,6.0 and 7.0.
Note: Indicate the CallServer power type and Model including Geo Redundancy.
See 5.0 Vintage Requirements.
Note: Download the latest software, patches, and loadware at:
http://www.avaya.com
| Audit the Software upgrade package |  |  |  | Date:
1. Verify that media containing the CURRENT software is available.
2. KDIF keycode check: SLT Levels and Package audit.
3. Verify the correct hardware components (such as RAM or Dongles) are present.
4. Verify minimum vintages for existing hardware are in place.
5. Download software deployment packages from support.avaya.com
6. PEP and Loadware Library (ESPL)
a. Download current Linux Base Patches, Deplists, Loadware and Site Specific PEPs.
| Obtain current NTPs from AVAYA |  |  |  | Date:
Reference documentation for Communications Server 1000 6.0, 7.0 and 7.5 can be found at:
http://support.avaya.com
IMPORTANT!
| Create an IP Address Spreadsheet |  |  |  | Date:
Document the following for each element/device.
ELAN / TLAN / CLAN IP Addresses
MAC Address
Host Name / Alias Name
Subnet Mask / Gateway
FQDN for the security Server
Node IP
Note: Ensure the planned network subnet configuration will support any
additional IP Addresses required for the upgrade and to allow for future expansion.
| Ensure that sufficient and the appropriate type of removable media is available |  |  |  | Date:
1. The 128MB RMD is used to backup the call server database
2. The Software Delivery Card (SDC) contains the following:
a. An Avaya CS 1000E Release 7.5 software
b. keycode files
c. CS 1000E Release 7.5 Dependency List (PEPs) for Large and Small
systems.
d. default database (if initiated during the installation)
3 The 1GB FMD is the hard drive for the CP PM Call Server.
Note: The 1GB CF FMD is required for a SA or HA CP PM configuration.
Note: For CPPM Linux , it is required that 2GB CF cards are used.
| Install new hardware if possible |  |  |  | Date:
1. Rack and power up any new hardware that can be, without impacting the system.
2. Upgrade memory on any Elements that are below minimum requirements.
Each element will need to be removed from service to complete this work.
The maintenance window(s) should be scheduled to occur prior to the work window.
| Have DNS Servers been identified for use with the Communications Server 1000 system? |  |  |  | Date:
| Has the DNS Database been created/updated with the TLAN information? |  |  |  | Date:
| Has the FQDN to be used with the Communications Server 1000 system been identified? |  |  |  | Date:
Note: If no DNS server is available, the DNS information must be added in Linux Base.
The host names are always related to the TLAN IPs only. Never add ELAN IPs to the
host file or any DNS server unless performing a managed services LAN configuration.
The host table on the managing PC should also be modified with the FQDN information.
| Does the system currently have PI or Site Specific patches installed? |  |  |  | Date:
If yes, cross reference the ESPL to ensure Release 6.0 versions (if applicable) are
obtained prior to the work window.
https://espl.avaya.com/espl/
If a patch rewrite is required, contact Avaya to determine the lead time before
scheduling the installation or upgrade.
| Have you attached a printout of all patches applied (MDP ISSP from all elements)? |  |  |  | Date:
| Have phones and personnel been identified for post-work testing purposes? |  |  |  | Date:
Phone 1:
| Terminal Number (TN): | Tester:
Directory Number (DN):
Phone 2:
| Terminal Number (TN): | Tester:
Directory Number (DN):
CS 1000 (forty-eight to twenty-four hours prior to work window) | [5 empty] | Date of availability
Note: This is your restore point in the event back out procedures are required.
| It is imperative that ALL system components that have the ability to |  |  |  | Date:
export/backup their DB are touched at this time.
| Test the DNS server database |  |  |  | Date:
1. Ping all FQDNs. Entries for elements not yet installed or upgraded will not respond,
however the name will resolve to the correct IP Address.
2. If any of the FQDNs do not resolve, correct the DNS DB prior to the upgrade window.
| Perform backups on all elements and applications using removable media. |  |  |  | Date:
Keep these backups in a secure location.
1. LD 43 EDD for all Call servers. Retain backup of database in secure location
2. If the upgrade is from a Linux server( available from 5.X and up), perform a sysbackup –b
on all Linux Elements AFTER the EDDs have been completed.
3. Backup the NRS database
4. Backup PD database - note Release 6.0 and above require a SPTP server
Note: Do not rely on TM backups, ensure true EDDs are taken.
| Test CLI access (local and remote) to ALL CallServer cores and elements |  |  |  | Date:
| Ensure a bridge number or some other coordinated call has been arranged |  |  |  | Date:
Contact Center readiness
| Is Contact Center currently installed? |  |  |  | Date:
| Will a new version of Contact Center be installed as part of this work? |  |  |  | Date:
Note: The minimum version of Contact Center supported is 6.0
Note: Ensure the Patching levels are current for CallPilot. Some patches may be
required for proper interoperability with the new release.
CallPilot readiness
| Is CallPilot currently installed? |  |  |  | Date:
| Will a new version of CallPilot be installed as part of this work? |  |  |  | Date:
Note: The minimum version of Callpilot supported is 4.07.
Note: Ensure the Patching levels are current for CallPilot. Some patches may be
required for proper interoperability with the new release.
Telephony Manager readiness ( Not supported on 7.X)
| Is Telephony Manager currently installed? |  |  |  | Date:
| Will a new version of Telephony Manager be installed as part of this work? |  |  |  | Date:
Note: The minimum version of Telephony Manager supported is 4.0.
Note: Ensure the Patching levels are current for Telephony Manager. Some patches
may be required for proper interoperability with Communications Server 1000 6.0,
not supported with 7.X.
Network
| Is the network using Access Control Lists (ACL's)? |  |  |  | Date:
If so, you will need to contact your Network Administrator and have the MAC addresses of the
new equipment added to the ACL's.
Customer's LAN based database

## System + Site Requirements
◄ Back to table of contents
System and Site Requirements
For additional information see:
Avaya Communication Server 1000E: Planning and Engineering (NN43041-220 )
Avaya Communication Server 1000E: Installation and Configuration (NN43041-310)
Meets specifications:
Equipment room environment
1. Temperature is maintained between 15° and 30°C (59° and 86°F)
Absolute temperature: Temperature does not go below 10°C (50°F) or above 45°C (113°F).
Equipment is never exposed to absolute temperature limits for more than 72 hours. [Major]
2. Environment temperature for telephones is 0° to 50°C (32° to 122°F).
3. Heat sources (such as floor heaters) are not placed near the equipment.
4. Temperature does not deviate any more than 10°C (18°F) within any hour.
The temperature differential in the equipment room does not exceed ±3.0°C (±5°F).
A temperature of 22°C (72°F) is recommended.
Temperature: _______° (Indicate C or F) [Major]
5. Humidity level for equipment: RH 20% to 55%, noncondensing
Absolute humidity level: Humidity level must not go below RH 20% or above 80%,
noncondensing Humidity ___________% [Major, Critical if more than 95% or less than 5%]
6. Environment does not show any visible signs of moisture. [Critical]
7. Ventilating openings on equipment are free of obstructions. [Major]
8. The room is clean, relatively dust-free, and well ventilated. [Minor, Major if concrete dust]
9. Equipment location is not subject to constant vibration. [Major]
10. Equipment is located at least 12 ft (3660 mm) away from sources of electrostatic,
electromagnetic, or radio frequency interference. [FCC CFR 47 Part 15 for
Class A devices. (<20 milliGauss ELF)] [Major]
11. Equipment is not located under liquid-carrying pipes. [Major]
12. Equipment room is not conducive to generating electrostatic discharge (ESD) [Major]
13. Antistatic wrist straps, sprays, mats, or a combination of these is in
evidence on-site. [Recommendation]
14. Switch room door has a lock installed. [Minor]
15. Electric locks, such as push button access code or card reader locks are not in use
unless a battery backup or a key override is provided.
16. No tripping or safety hazards exist in the equipment room. [Major]
17. Installation is not located close to sources of EMI or RFI, such as high-voltage power lines,
radar, broadcast stations, mobile communications, power tools, appliances
(such as vacuum cleaners), and office business machines (such as copiers),
industrial machines and ultrasonic cleaners, vehicle ignition, arc welders,
dielectric heaters, and dimmer switches. [Major]
18. Lighting illumination is 50 to 75-ft candles measuring 76 cm (30 in.) above
the equipment room floor. [Recommendation]
19. Equipment room is protected from receiving direct sunlight. Direct sunlight is prevented
from shining on electronic hardware, especially disk units. [Major]
20. Adequate floor space has been made available to install equipment racks,
patch panels, power systems (UPS), and so on. [Major]
21. Flooring is sealed concrete, vinyl, or mastic tile.
22. RS-232 terminal and communications devices must not exceed the 50-ft cable length limit
unless line drivers are utilized. [Major]
23. The storage room for spare parts is secure. [Recommendation]
24. If it is not possible that the site maintain the environment of the storage area exactly
the same as the environment of the operating equipment, stored materials are allowed
time to adjust to the equipment room environment before using them. [Major]
25. The storage area is dust-free and away from high humidity and machinery
such as electric motors of transformers. [Major]
26. Circuit cards that are not in use are stored in a protective antistatic bag. [Major]
27. Media Gateway, Call Server covers, UEM/IPE Shelf and Cabinet covers are installed. [Major]
28. Equipment rear and front clearance must be 36" and side clearance must be 12". [Major]
Reserve power equipment room
29. If the reserve power equipment is located in a separate room, then that room is:
• well-ventilated and operating at optimum temperature;
specific gravity readings are based on 25° C (77° F)
• equipped with protective equipment (such as goggles, face shields, acid-resistant gloves,
protective aprons, water for rinsing eyes/skin, and bicarbonate of soda)
• well-secured
• accessible (the doorway must not be blocked)
• in compliance with all floor loading requirements and the noise levels required by
OSHA standards 1910.5 (or local standards)
Maintenance and technician area environment
30. A locking cabinet or storage area is in place for backup disks. [Recommendation]
31. The area contains a table or desk terminal, printer, or equivalent device. [Recommendation]
32. Maintenance workstation is equipped with a: [Major]
• dial-up modem or connection to the network;
• terminal emulator application such as Telnet or rlogin;
• Web browser;
• operational maintenance telephone
33. Observations or comments:

## Power & Grounding
◄ Back to table of contents
Power and Grounding
Complete this checklist to ensure that electrical power and grounding standards for Communications Server 1000 are met.
Check the items in the checklist to confirm that they have been completed. Provide additional information where requested.
This checklist is to be completed and verified during coordination conference calls.
The Installation Coordinator is responsible for forwarding copies of this document to parties involved with installation.
Note: According to Avaya Communication Server 1000E: Planning and Engineering (NN43041-220), Avaya recommends
using an isolated ground topology as the preferred method of grounds for use as the CS 1000E single-point ground source.
In the absence of such facilities, a portable or hardwired UPS system can be used. It is preferable that UPS systems
contain load isolation transformers in their design.
Isolated Ground topology is not accepted in Canada according to code.
For additional information see:
Avaya Communication Server 1000E: Planning and Engineering (NN43041-220 )
Avaya Communication Server 1000E: Installation and Configuration (NN43041-310)
The responsibilities for completing this checklist are as follows.
| Checklist section | To be completed by Distributor (Switch Tech) | To be completed by Customer
CS 1000 System AC service panel
AC Power and Ground Worksheet
System power and ground connections
CS 1000E System AC service panel
Meets specifications:
1. The AC supply conductors are dedicated and uninterrupted from the building primary
source or transformer to the PBX main AC service panel.
(This does not apply to subpanels). [Major]
2. Verify that an Isolated Ground (IG) or ACEG conductor is installed from MGN/ X0 to an IG or
ACEG bus in the AC panel serving the PBX equipment room. This point becomes the
single-point ground reference for the PBX.
Note: In some cases an AC panel is not a requirement. Various UPS systems establish
the same intent and purpose as the panel IG/ACEG bus. The engineer performing the
evaluation must research the application and determine its intent. [Critical]
3. The IG/ACEG conductor is sized per code. (NEC 250).
Note: It is recommended that the ACEG conductor be the same size as the largest
phase conductor. [Major]
4. The IG/ACEG conductor runs in the same raceway (conduit) as the phase and neutral
conductors (NEC 250). [Major]
5. The IG/ACEG conductor is insulated, permanent, and continuous (no splices). (NEC 250) [Major]
6. A dedicated AC panel is installed in the PBX room for the CS 1000E and associated equipment
only. Circuits being served for purposes such as lighting, air conditioning, heating, generators,
copiers, or motors from the CS 1000E service panel are not recommended. Panel ID: [Major]
7. Circuit breakers are identified and labeled at the AC service panel. (NEC 110-22) [Minor]
8. Ensure that all voltage and current levels recorded are within the defined limits.
Note: A licensed Electrician must obtain these results. See the AC Power and
ground worksheet [Critical]
9. The workspace clearance around the AC service panel is 3-ft. (NEC 110-26) [Major]
10. All RS-232 ancillary devices connected to the system I/O circuit cards must be wired from the
same AC panel as the PBX power supplies, with individual hot, neutral, and isolated
ACEG ground wires.
11. The following current, power, and cooling requirements are met for Communications
Server 1000 components:
12. The following power and cooling requirements for Media gateway packs are met:
13. Power from each outlet meets the input requirements of at least one CS 1000E power
supply listed in the following tables (continued):
14. Power from each outlet meets the input requirements of at least one CS 1000E power supply
listed in the following tables (continued):
Location of power outlets:
Note: The maximum distance between a power outlet and the system equipment is met, in
relation to the length of the power cord.
• In North America, the power cord is 9 ft, 10 in. (3000 mm).
• Outside North America, the power cord is 8 ft, 2 in. (2490 mm).
15. Observations or comments:
AC Power and Ground Worksheet
AC Service Panel Measurements
Note: If a portable UPS system is used, measurements are only taken on the input/output
voltage and the neutral ground voltage. Percent of load must also be notated.
Note: The neutral current must never exceed the current in any single-phase leg. A licensed electrician must take
AC service panel measurements. Voltage and current values must comply with technical documentation.
Voltage between neutral and ground can signify poor or loose connections or noncontinuous grounding.
Current flow in the grounding conductor can indicate that the neutral has been used for equipment grounding.
If currents are balanced in a three-phase system and there is significant neutral current, then harmonics are present.
Harmonics can deteriorate transformers over time by overheating their internal wiring.
Solution: Use transformers specifically designed for harmonic loading (k-factor-rated).
System power and ground connections
1. The Signaling Server power cord is plugged into the AC outlet of the rack and the AC outlet
of the rack is grounded to its dedicated electrical panel. [Major]
2. In a system with more than one MG 1000E powered by multiple service Panels,
a #6 AWG (#40 Metric Wire Gauge) ground wire from the rear panel grounding lug of
each MG 1000E is connected to an NTBK80
Ground Bar. The ground bar is connected to the Single Point Ground reference. [Major]
Note: In the UK, the ground wire from the CS 1000E equipment is connected to an NTBK80
Ground Bar or through a Krone Test Jack Frame.
3. The Communications Server 1000E systems have ground lugs on the chassis, cabinet
and MG 1010 and must be grounded via #6 stranded conductor.
The media gateways must be grounded using the following guide:
• MG1010 (NTC310) will have a single ground conductor to SPG
• NTDU14 chassis will have a single ground conductor to SPG
• NTDU15 chassis will have a single ground conductor to NTDU14
• NTDK91 chassis will have a single ground conductor to SPG
• NTDK92 chassis will have a single ground conductor to NTDK91
• NTAK11 cabinet will have a single ground conductor to SPG
** Screw connections to the 19" rack should never be used to provide a ground connection
for Avaya equipment.
** Ground conductors should never be daisy chained expect in the specific scenario above where
the NTDU14/15 pairs are used.
** If a UPS is being used, the SPG ground bus needs to source from the same electrical service
panel as the UPS.
4. If multiple pieces of equipment are installed in a rack, a separate connection is run from the
grounding lug on each piece of equipment to the NTBK80 Ground Bar. [Major]
5. In an installation where a dedicated panel cannot provide optimal conditions, a load
isolation transformer or load isolation transformer-based UPS/Line conditioner with the
following characteristics is used: [Major]
• 120/208/240 V AC input, over-current protected at primary
• 120/208/240 V AC available at secondary outputs, each circuit breaker protected
• primary and secondary windings are completely isolated from one another
• the load isolation transformer or load isolation transformer-based UPS/Line conditioner is
approved for use locally as a stand-alone user product (CSA, UL, or other locally recognized
clear markings)
• the load isolation transformer or load isolation transformer-based UPS/Line conditioner is
capable of providing power to all CS 1000E components operating at the same time at full load
• equipment unrelated to the CS 1000E is not powered from a transformer that provides
service to the CS 1000E system
• the load isolation transformer or load isolation transformer-based UPS/Line conditioner is
electrostatically shielded to minimize ELF fields
6. Ground conductors are at least #6 AWG (16 mm2) at any point.
7. Ground conductors do not carry current under normal operating conditions.
8. Spliced conductors are not be used. (Continuous conductors have lower impedance
and are more reliable.)
9. All conductors terminate in a permanent way. All terminations are easily visible
and available for maintenance purposes.
10. Ground connections are tagged with a clear message such as
“Critical Connection: Do Not Remove or Disconnect”.
11. The installation meets the specific grounding requirements for the area: [Major]
12. A 120VAC non-switched receptacle is provided within 9 ft of the CS 1000E cabinets. It
is strongly recommends that each Media Gateway and Media Gateway Expansion pair for
1000E systems are powered from one dedicated 120VAC, 15/20 amp branch circuit with
individual hot, neutral, and AC equipment ground or isolated ground wires. Installation does
not exceed 80% of the maximum branch circuit or UPS load rating. [Major]
Media Gateway
13. The NTBK80 ground bar is capable of grounding up to six Media Gateways (either with
or without companion Media Gateway Expanders) back to the SPG. If there are more than
six Media Gateways (either with or without companion Media Gateway Expanders),
the NTDU6201 ground bar is used.
14. The NTDU6201 can be adjusted for various mounting configurations. It accepts 35 #6 AWG
(16 mm2) wire connections. The ground bar terminates at the service panel ground.
15. All equipment located in a series of equipment racks that are physically bonded together
are grounded to and powered by the same service panel.
16. If additional service panels are required, they are collocated beside the original service panel.
17. If racks are not bonded together, then the equipment located in the racks can be grounded
and powered by separate service panels.
18. A #6 AWG (16 mm2) ground wire is connected from the rear panel grounding lug of each
Media Gateway to the ground bar.
19. The ground bar is connected to a ground source in the dedicated service panel.
Note: In the UK, the ground wire is connected from the equipment to a ground bar or through
a Krone Test Jack Frame.
20. The Media Gateway and Media Gateway Expander are considered as the same ground. To ground
the Media Gateway Expander, the ground wire is jumpered from it to the grounded Media Gateway.
21. Multiple pieces of equipment installed in a rack are grounded with a separate connection from the
grounding lug on each piece of equipment to the ground bar.
22. If a piece of equipment in a rack does not have a grounding lug, the rack is grounded to the ground bar.
23. For all CS 1000E system ground paths, route the correct size of insulated copper conductors is
routed inside conduit.
24. Each Media Gateway and Media Gateway Expander pair is powered from the same service panel.
25. A dedicated electrical panel that is connected to the facility’s electrical system is used to power
the system and this panel provides power only to the CS 1000E system components and
related telecommunications hardware such as TTYs and printers. [Recommended].
26. A system ground conductor, sized at a minimum of a #6 AWG stranded, insulated wire is installed
from the cabinet ground bus to the ACEG bus in the AC panel. Where UPS systems are
employed, a #6 AWG wire can be installed from the cabinet ground bus to the grounded
metallic case of the UPS using a ground lug. [Critical if missing; Major if undersized].
27. A #6 AWG insulated, stranded conductor is installed between each CS 1000E cabinet
ground lug and the cabinet ground bus. [Major]
28. All grounding conductors are clearly identified and labeled. [Minor]
29. No telecommunications ground bus of the CS 1000E is connected to untested horizontal structural
steel, water pipes, or other unreliable ground paths. [Major]
30. The cabinet ground bus is mounted near the CS 1000E cabinets. [Major]
UPS requirements
31. Cabinets are grounded to the same AC service panel or UPS that provides input power to
the PBX system. [Major]
32. All UPS systems must have a ground lug (to accommodate a minimum of #6AWG wire)
or ground bus installed and bonded to the UPS metallic enclosure to allow connections to
the PBX system ground bus and the AC panel ACEG bus.
Note: If the UPS system is equipped with an isolation transformer, the ground lug or bus must be
wired from the center tap (X0) of the transformer (The ground lug or bus allows a parallel connection
to the CS 1000E single-point ground source in case the UPS power cord is unplugged). [Major]
33. #6 AWG grounding conductors are installed from the UPS ground bus or lug to the CS 1000E
cabinet ground bus and the ACEG bus in the AC service panel. See items #3 and #10 above. [Major]
34. CSUs (Channel Service Units) are connected to reserve power (UPS) or are span powered. [Major]
35. Equipment unrelated to the CS 1000E system in any way is not powered from the same
120 VAC receptacles or UPS system as the PBX. [Major]
36. In isolated ground environments, other equipment, equipment racks, or metallic conduit
do not come in contact with the CS 1000E equipment rack. [Major]
37. The earth source, which the CS 1000E system connects to through the AC service panel, has a
resistance of 5 ohms or less. [Major]
38. Ground conductors are insulated, permanent, and continuous (not spliced). [Major]
39. All terminations are easily visible and accessible for maintenance purposes. [Major]
40. The dedicated service panel feeds only the CS 1000E and is located as close to the
system as possible.
41. Each vertical power bar on the 19-inch rack has its own power feed.
42. The system ground conductor is insulated, and the same size as the largest conductor and runs
between the Main Service Panel (MSP) and the CS 1000E panel.
43. Ground conductors are not smaller than #6 AWG.
44. Electrical layout is reflective of a typical ANSI/EIA/TIA607 installation with TMGB and
TGB ground blocks.
45. If installation is not at a ANSI/EIA/TIA607 site then a wire is connected from system
ground bar to AC Ground at the Service panel.
46. Ground and Neutral bonding occur at either the transformer or at the first disconnect
(Main Service Panel).
47. The resistance between the ground post of any equipment and the single-point ground to
which it connects is less than 0.25 ohms for an installed Call Server, MG 1000E, MG 1000E
Expander, or Signaling Server. [Major]
48. The installation uses one of the following bus bars as a system SPG: [Major]
• building principal ground, normally in a building with one floor
• floor ground bar, normally in buildings with more than one floor
• dedicated TMGB/TGB bonded to the building grounding system
• ACEG bus located inside the PBX service panel
Other items
49. QUA6 Power Failure Transfer Units (PFTU) are available to transfer trunk lines during a power
or system failure. [Recommendation]
Note: The appropriate AC power cord kit is used for the installation as listed in the following table.
(These cords connect a CS 1000E system to a commercial AC power source.)

## Cabinet installation
◄ Back to table of contents
Cabinet installation
For additional information refer to:
Avaya Communication Server 1000E: Installation and Configuration (NN43041-310)
Meets specifications:
1. Circuit cards are of allowable vintage (no outstanding Product Advisories or Bulletins). [Major]
2. Circuit cards are locked into place. [Minor]
3. All MDF/IDF blocks are clearly labeled. [Major]
4. PBX cabling is not strapped to the exterior of any conduit or raceway as a means
of support. [Major]
5. MICB cards, where installed, use cards slots 1, 2, 3 in Media Gateways and
slots 7, 8, 9 in Media Gateway Expanders only. [Major]
6. M2250 consoles utilize 5 consecutive TN units and are properly cross-wired with three power TNs.
The AUX cable can be utilized to take the place of two power TNs only. See console
cable wh/sl, rd/or, & rd/grn pairs. The M2250 consoles do not require a static discharge
ground connection, the connection should be installed to protect any earlier vintage attendant
consoles that may be used as replacements. [Major]
Application tapes and messaging system tape cartridges
7. Media is not subject to rapid changes in temperature or humidity. [Major]
8. Media is kept away from strong magnetic fields. [Major]
9. Database backups are routinely performed and are readily available. [Major]
10. System installation CDs, PC cards are available for the PBX and Applications
products in the event of severe system hardware malfunction or data corruption. [Critical]
11. Observations or comments:

## Cabling installation
◄ Back to table of contents
Cabling installation
For additional information refer to:
Avaya Communication Server 1000E: Installation and Configuration (NN43041-310)
Meets specifications:
Outside plant cabling and protectors
1. Entrance cable sheath is grounded as close as possible at the point of entry to an
approved ground source. [Major] (NEC 800-33; 40)
2. Splice cases are properly grounded. [Major]
3. Approved protection devices are used for Telco network and campus cables. (Carbon,
Gas tube type for network cables; fast-acting, low let-through type on campus cables).
(NEC 800) [Major]. For further details, see Product Bulletin 97040 (April)
revision 1 relating to protection.
4. Protection devices are installed at both ends of a cable in a campus environment.
(Silicon Avalanche type. see Oneac 5SDP; 5SAP) [Major] ANSI/UL 497-1995 Specs -10V
for digital telephones; 48VDC for analog telephones. For further details, see Product
Bulletin 97040 (April) revision 1.
5. All protection device grounding conductors are grounded to an approved source with an
appropriately sized wire. The grounding conductors must be kept as short and straight as
possible. (No sharp bends- 8 radius) (NEC 800-40) [Major]
Cabinet cabling
6. Cabling must be installed in a neat and orderly fashion. [Major]
7. MDF cables are seated and secured in place using factory velcro straps. [Major]
8. All cables for cabinets, Call Servers, Media Gateways/Expanders, Signaling Servers
(SDI, AUX, VGMC ELAN/TLAN, CE-MUX, DS-30X, and 10/100BaseT cables)
and adapters are properly fastened. [Major]
9. Power wiring must not be installed in a parallel fashion with CAT5 cabling. Installing power wires
perpendicular to CAT5 cables is preferred and minimizes effects from EMI or ELF fields. [Major]
10. EMI mitigating ferrite rings (NTVQ83AA) are installed on Voice Gateway Media Card
TLAN/ELAN patch cables. [Major]
11. NTCW84JA assemblies are used for each VGMC connector. [Major]
12. CAT5 patch cables are not installed near fluorescent lighting fixtures. [Major]
13. ELAN/TLAN patch cables for VGMC and Signaling Server hardware are factory made
and kept at 20 cable feet or less. [Recommendation]
14. All patch cables are labeled and correlate to a network infrastructure diagram
or schematic. [Minor]
15. The NTDK95 CE Mux cables, between the Media Gateway and Media Expansion Cabinets,
must be installed in the correct direction during Chassis Expansion Cabling installation.
If installed in reverse, can result in product malfunction including: low audio; garbled transmission
from IP to TDM phones; dropped calls; and invalid card responses.
Attach the Expansion Cabinet connecter to the NTDU15 unit. If no labels are present, the
Expansion Cabinet contains a ferrite bead on a single wire. For more information,
please see Bulletin 2008008579.
Cross-connect terminal requirements
16. To allow for future expansion and equipment changes at the cross-connect terminal,
the cross-connect terminal has enough space for connecting blocks to terminate
four 25-pair cables from each Media Gateway and for each Media Gateway Expander.
[Recommendation]
17. When Ethernet connections are used instead of traditional cabling, the Media Card
Input/Output adapter is used:
• for the 1.5 Mbit DTI/PRI circuit card NTRB21, NTBK04 cable is used
• for the 2.0 Mbit DTI circuit card NTAK10, 2.0 Mbit PRI circuit card NTAK79, and
2.0 Mbit PRI circuit card NTBK50, NTBK05 cable is used
• each IPE card slot equipped with a Line or Trunk card uses a 25-pair cable from
the host Media Gateway or Media Gateway Expander
• four conductors for the AUX cable run from the Media Gateway.
• one 25-pair cable runs from each Power Fail Transfer Unit (PFTU) QUA6
• wiring is in place from telephones and trunks.
18. In the UK:
If the Krone Test Jack Frame is used, only authorized personnel are allowed access the
Krone Test Jack Frame and it is installed in a locked room or in an environment that
prevents free access to the equipment.
For additional information about the cross-connect terminals, see Avaya Communication
Server 1000E: Installation and Configuration (NN43041-310). [Major]
19. Observations or comments:

## System operation
◄ Back to table of contents
System operation
For additional information refer to:
| X11 Software General Release Bulletin (shipped with new software) | Meets specifications:
System diagnostics
1. LD 30 Network and Signaling Diagnostic (NWS). [Minor]
2. LD 34 Tone and Digit Switch and Digitone Receiver (TDS). Check results from the midnight
routines. [Major]
3. LD 37 Input/Output Diagnostic (IOD). Use STAT command for TTYs. [Major]
4. LD 38 Conference Circuit Diagnostic (CNF). Check results from the midnight routines. [Major]
5. LD 43 Data Dump (EDD). Check for successful completion of a manual data dump. [Critical]
6. LD 44 Software Audit (AUD). Must be configured in BKGD of Ld-17. Check for normal
AUD000 messages. [Major]
7. LD 48 Status of ELAN and Mail/ESDI Links. Make sure all AMLs that are in use are Active
Empty. [Major]
8. LD 60 Digital Trunk Diagnostic (DTI/PRI). Use the SSCK command to check system clocks. Locked
on to IP daughterboard #1. Also check midnight routines for frame slips, CRC errors. [Major]
9. LD 117 STAT HOST
10. LD 137 ELNK STAT ELNK command
11. GTR, documentation, and Backup logs are located in switch room.
Note: Ensure appropriate level and system type of technical documents are available. [Minor]
12. The PBX maintenance modem and terminal server performs as expected. [Major]
13. A terminal server or SEB modem is configured as to allow Telnet access to the
system. [Recommendation]
14. The system is equipped with a working maintenance terminal and printer. [Major]
15. A PC is available on location in order to access Element Manager and NRS [Major]
16. Minimum level PEPs are installed in the system. This includes DepList PEPs for the
Call Servers, required PEPs for Signaling Servers, and Voice Gateway Media Card PEPs.
[Recommendation]
17. IP telephones are on the latest recommended firmware. [Recommendation]
18. Signaling Servers are load sharing (equal number of registered IP phones) [Recommendation]
19. Printouts of Signaling Server config.ini and bootp.tab files are readily available.
pdt> cd /u/config, copy config.ini, copy bootp.tab [Minor]
Memory Size
20. The installation meets the minimum memory requirements.
21. The installation does not exceed the recommended maximum call register count.
22. Observations or comments:

## System software
◄ Back to table of contents
System software
Meets specifications:
Overlay 15/21 Customer Data Block
1. SRCD (Auto Set Relocation Code) has a value programmed. [Major if SPRE is 1, Minor if other]
Overlay 17/22 Configuration Record
2. Daily Routine defined as LD 34, 38, 60,137. [Major]
3. LD 44 in background routine. [Major]
4. The number of call registers (NCR) within the maximum value required by GRB documentation regarding
port size and features used. 1000M- 800 call registers [Major]
5. 1000M LPIB and HPIB values equal 450. [Recommendation]
6. History file is defined as MTC, BUG and is set at minimum length of 60 000 characters. [Major]
7. ERRM is configured as ERR, BUG, AUD. [Major]
8. RLS IDs are configured for each D-Channel where appropriate. [Major]
Overlay 11/12/13 digital telephones, attendant consoles, and digitone receivers
9. Switchroom phone requires MTA for class of service. [Major]
10. Consoles powered through unused TNs are correctly programmed PWR. [Major]
11. Consoles are cross-wired properly and must utilize consecutive units. [Major]
12. The PBX maintenance modem and terminal server performs as expected. [Major]
13. Observations or comments:

## VoIP Networking Parameters
◄ Back to table of contents
Networking parameters for VoIP
If Avaya Aura System Manager is to be deployed, the server should be located on the CLAN subnet. The TLAN and ELAN subnets should
be made routable through a Layer 3 routing device. This configuration will allow System Manager access to the TLAN and ELAN elements
without exposing the core system structure to CLAN traffic (including Broadcast, Multicast and DHCP). It is further recommended that
a security policy such as an Access Control List (ACL) or equivalent be put in place to prevent unauthorized users or devices from entering
the ELAN or TLAN subnets.
Meets specifications:
1. A LAN or WAN assessment has been performed on the customer network. [Critical]
2. The layer 2 switch ports are in place for the CS 1000E ELAN/TLAN are configured
for auto, autonegotiate. [Major]
3. The layer 3 switch ports are in place. [Major]
The ELAN subnet contains only Communications Server 1000 equipment. Do not expose the
ELAN subnet to any non-Avaya broadcasts, multicasts, or DHCP packets.
The TLAN subnet is an isolated VOIP network that contains only the Communications Server 1000
elements, peripherals, and user endpoints. Configure peripherals and user endpoints, such as
IP Phones, and soft phones in an additional isolated network subnet or in the CLAN.
The CLAN is any customer subnet outside of the ELAN and TLAN subnets.
The CLAN subnets are part of the customer's pre-existing network configuration.
The ELAN, TLAN and CLAN subnets must be separated by layer 3 routing.
4. The ELAN subnet and the TLAN subnet are on separate subnets. [Major]
5. All applications on the ELAN subnet are on the same subnet. [Major]
6. VGMC circuit cards in the same node are on the same TLAN subnet. [Major]
7. Minimum of one DSP resource for every TDM port (T-1 trunks, digital phones,
analog phones, analog trunks, Avaya CallPilot channels). For non-blocking requirements
one DSP per TDM port is a best practice. [Recommendation]
8. Layer 2 switches derive UPS power from different branch circuit sources, if possible, in order to
minimize single-points of failure. [Recommendation]
9. Layer 3 switches derive UPS power from different branch circuit sources, if possible,
to minimize single-points of failure. [Recommendation]
10. Observations or comments:

## Product Bulletins
◄ Back to table of contents
Product Bulletins for vintage and release updates
| Product Bulletin | Affected Product | Part Description | Defective Part # | Replacement Part # | Reason for Change

## Remote access
◄ Back to table of contents
Remote Access and Remote Access Service
Complete this checklist to ensure proper configuration of remote access to Communications Server elements and applications. If using Remote Access Service (RAS), two IP addresses must be provided to set up RAS for dial-in support. These IP addresses should be in sequence, and on the Nortel server subnet.
Check the items in the checklist to confirm that they have been completed. Provide additional information where requested.
This checklist is to be completed and verified during coordination conference calls.
The Installation Coordinator is responsible for forwarding copies of this document to parties involved with installation.
The responsibilities for completing this checklist are as follows.
| Checklist section | To be completed by Distributor | To be completed by Customer
LogMeIn Support
Direct modem access
RAS
Other remote access support
LogMeIn Support |  |  |  |  | Date of availability
| Internet Access to http://www.logmein123.com - confirm site access |  |  | Date:
Validate LogMeIn Support is viable
Note: This will require the site to establish a session with NRIUS support
prior to the date of the work window.
Direct modem access |  |  |  |  | Date of availability
| Note: If you are using a modem, ensure the modem is connecting directly to the server being accessed. |  |  | Date:
What Communications Server 1000 elements will NRIUS have access to?
Note: If modem assess is available to the CLI of the Primary Security Server, support will be able
to SSH to any registered device
RAS access |  |  |  |  | Date of availability
| What network subnet range(s) will be accessible via RAS? |  |  | Date:
Note: Two local IP Addresses will be required to setup RAS for dial-in support.
IP address assigned to RAS user (NRIUS) must be part of the Nortel subnet being worked on.
These IP Addresses should be sequential.
Other Customer Provided Remote Access |  |  |  |  | Date of availability
| Please detail any alternative modes of remote access that can be provided: |  |  | Date:

## Example Timelines
◄ Back to table of contents
Upgrade Order of Operation and Estimated timeframes
The order of operations described below are examples only.
This document in no way defines a mandatory methodology for an upgrade.
The order of operation and overlap will depend on the number of personnel and state/type of system to be upgraded.
The times and tasks included in the two examples below do not include additional tasks and timeframes required
to prep and test applications such as CallPilot, Contact Center and other third party applications.
Single Communications Server 1000 system installed at a single site
The below estimated timeline assumes a Communications Server 1000 system at a single site with the following components running
RLS 5.xx and one technician performing the work with no multitasking.
1. 1 CPPM HA CallServer
2. 2 TPS CPPM Signaling Servers
3. 4 MC32S VGW elements
| 1:30 | Install UCM Server (Primary Security Server)
(Linux Base, BIOS, Application/Database and Patching)
| 1:15 | Upgrade CallServer Core1 (Inactive Core)
(Linux Base, BIOS, Application/Database and Patching)
| 1:15 | Upgrade Follower Signaling Server
(Linux Base, BIOS, Application/Database and Patching)
| 1:15 | Upgrade Leader Signaling Server
(Linux Base, BIOS, Application/Database and Patching)
| 0:30 | Upgrade MC32S cards (5 card simultaneous with 10 cards total)
| 0:30 | Perform middle of the road acceptance testing.
(Point of no return – back out here if test results require)
| 1:00 | Upgrade CallServer Core0
(Linux Base, BIOS, Application/Database and patching)
| 0:30 | Acceptance Testing
7.5 Hours total estimate with no lunch break.
Single Communications Server 1000 system installed at a multiple sites
The below timeline assumes a Communications Server 1000 system at multiple locations with the following components running RLS 4.xx and
three technicians performing the work with multitasking. Both NRS are Co-Res, one at the Main Site and the other at Site #1.
1. Primary CPPM HA Callserver at main site
2. Alternate CPPM N-Way CallServer #1 at site #1
3. Alternate CPPM N-Way CallServer #2 at site #2
4. Secondary CPPM N-Way CallServer #1 at site #3
5. 2 TPS CPPM Signaling Servers at main site (one is Co-Res NRS)
6. 1 TPS CPPM Signaling Server at each Alternate and Secondary site.
7. 4 MC32S VGW Elements at main site
8. 2 MC32S VGW Elements at each Alternate and Secondary site.
| 1:45 | Tech #1: Install UCM Server (Primary Security Server)
(Linux Base, BIOS, Application/Database and patching)
Tech #2: Upgrade CallServer Core1 (Inactive Core)
(Linux Base, BIOS, Application/Database and patching)
Tech #3: Upgrade Follower Signaling Server
(Linux Base, BIOS, Application/Database and patching)
| 1:00 | Tech #2: Upgrade Leader Signaling Server (CO-Res TPS/NRS)
(Linux Base, BIOS, Application/Database and patching)
| 0:15 | Tech #3: Upgrade MC32S cards (simultaneous)
| 0:30 | Tech #1: Perform middle of the road acceptance testing.
(Point of no return – back out here if test results require)
| 1:15 | Tech #1: Upgrade CallServer Core0
(Linux Base, BIOS, Application/Database and patching)
| 0:30 | Tech #2: Travel time to remote site #1
Tech #3: Travel time to remote site #2
| 2:00 | Tech #2 and Tech #3 work simultaneously on remote 1 and remote 2
Tech #2: Remote Site #1
Tech #2: Upgrade Alternate CallServer #1
Tech #2: Upgrade Signaling Server (CO-Res TPS/NRS)
Tech #2: Acceptance Testing
Tech #3: Remote Site #2
Tech #3: Upgrade Alternate CallServer #2
Tech #3: Upgrade Signaling Server
Tech #3: Acceptance Testing
| 1:45 | Tech #2: Remote Site #3
Tech #2: Upgrade Secondary CallServer #1
Tech #2: Upgrade Signaling Server
Tech #2: Acceptance Testing
| 0:30 | Travel time for Tech #2 and Tech #3 to return to Main Site
| 1:00 | Acceptance Testing
8.5 Hours total estimate with no lunch break.
Customer's LAN based database

## Gotchas
◄ Back to table of contents
Common Issues to be aware
This tab contains a list of items that if properly prepared for will make the upgrade go smoothly. This is not an all inclusive list, and is also
not intended to be used as a keystroke MOP for the solutions provided.
Core
| Customer | If an attendant console exists on the current install of the Communications Server 1000 system,
| Database | DO NOT choose Customer Database when upgrading to 6.0.
You must choose Default Database and complete the install (including the Deplist Refresh) prior to converting the
existing Database. PEP MPLR28682 MUST be present and active in the system prior to importing a customer database
that has an attendant console configured.
WARNING: Failure to do so, will corrupt the customer database.
If upgrading from a Pre- Release 4.5 to a system post 4.5 and the customer is using Symposium, they may need to turn on
CMB in ld 23 for any CDN that goes into the Symposium.
Note: LD23 prompt under the CDN section: Default is (NO) and from what the site is seeing, this should be set to (YES).
For each CDN that they want the correct redirection taking place CMB (NO) YES Deny or Allow redirection to
Control DN Mailbox.
Symptom: Call goes via CDN to an Agent to a Voice mail, the Voice mail box response id is for the Agent and not for the CDN.
If the customer desires it to go to the CDN VM then they will need to turn on CMB.
Symptom: Upgrading from Release 25.40 to 6.00 can cause Dial Tone and Ring Back to sound like European ( A-Law)
and not North American (Mu-Law).
Solution: Change the INTN (International Companding Law) from Yes to No and INIing the PBX.
| Credentials | Do not use an exclamation point as part of the admin2 password. The ! character will abort the registration process.
Do not use admin1, admin2, pdt1, or pdt2 as UserIDs in the UCM administrative users database.
Do not use admin or any other UCM UserIDs in the Communications Server 1000 native PWD database.
Do not use VxWorks UserIDs in the UCM database.
UserID conflicts causes security permission issues which may cause the system to deny access during critical
maintenance procedures.
Note: If admin2 UserID is even present and disabled in UCM prevents admin2 from logging into a VxWorks CallServer.
| FIJI | When single slot FIJI cards are deployed, the Loadware (version 29) must be manually
downloaded and deployed to allow the cards to complete the FDL process.
When seating the new single slot cards, use the following rules:
Core/Net: Slot 9 (leaving slot 8 empty)
Network: Slot 2 (leaving slot 3 empty)
WARNING: Do not use slot 3 or slot 8 for ANYTHING. These slots must be left empty at all times.
WARNING: All double slot FIJI cards MUST be updated to Loadware version 21 PRIOR to installing any single
slot FIJI cards. If this process is not done properly, the double slot FIJIs will not function correctly.
MPLR26629 can then be loaded. (note that MPLR26629 has been superseded by MPLR28213)
Note: If upgrading from IGS to FNF ensure the jumper RN27 at location E35 on all 3PE cards
are set to the "A" position.
| CPSI Ports | Also known as Core TTYs. Prior to upgrading, ensure that at least one CPSI port is defined in the ADAN database.
In an HA CallServer configuration, the upgrade will proceed as expected until the offline core boots into the new
release. At this time the installer will only have access to PDT. (no overlay loader prompt will be seen)
This is due to no CPSI ports being configured in the upgraded customer database. To resolve this the installer
create the CPSI port. must restore the old release of software or if the system had a PTY configured they could
access the upgraded core via PTY and then build the CORE TTY(s).
| 3PE's | The RN27 jumper needs to be on the A position (toward the faceplate) on ALL 3PE's
| Sys Util | With older Card Cages and CP IV you may encounter issues unless you have Sys Util Card.
| Card | You may get a Dongle error.
| Signaling Server | Associate the Signaling Server with the UCM Domain.
1. Logout of the existing local-login session.
2. Enter the server's network login address in the format https://<server address>/network-login.
3. Login using admin credentials, not admin2.
4. A list of UCM Elements appears
5. Under CS1000 Services on the left-hand menu, select Software Deployment.
6. When prompted, enter the admin credentials
CS 1000 elements to join the domain. Enter the admin credentials.
The Deployment View appears.
7. Make changes on the Deployment View screen.
a. On the right-hand side, change the view from Servers to CS1000 systems.
b. Click Add.
c. Enter the host name for the CS1000 System.
d. Enter an optional description if desired.
e. Click Next.
f. Validate the Keycodes.
g. Select the languages.
h. Select The database.
i. Add the Signaling Server.
1. Select this server from the drop down list of Signaling Servers.
j. Click Finish.
k. The Deployment View displays a CS1000 tree of elements.
l. Click UCM Network Services.
Pre-loaded Hard Drive
| BIOS | Any CPPM card used for Release 6.0 must be running version 18 BIOS. A fresh install of 6.0 will
automatically check the card and upgrade the BIOS for you, however if a pre-loaded hard drive is to be used,
care must be taken to ensure the BIOS is upgraded.
When using a pre-loaded HDD, take the following steps to ensure the BIOS is upgraded:
1. Boot the CPPM card, noting the BIOS version displayed during POST.
(BIOS version number is located in the bottom right corner of the POST banner.)
2. If a Linux Base SDC is not available on Site, Using a 2GB Compact Flash Card,
create an SDC using the current version of CardPro.
(Obtain the SDC software and the current version of CardPro from Nortel.com)
3. Boot the CPPM into the install program, enter the tools menu and select the BIOS upgrade option.
| Date/Time | When installing a pre-loaded HD into a CPPM or other compatible element, The initial password change may fail
with a message indicating the password is too new. This issue may occur when the element being used cannot
find a valid Time Server on the network.
To resolve this, manually change the Linux Date and then update the password.
MC32 (VGMC)
| Firmware | MC32 cards (either the NTVQ01BA or BB vintage) should be updated to the most current version of firmware.
Note that the BA vintage card has a different current version of firmware than the BB vintage card.
When performing the upgrade process as documented in NTP (553-3001-204 or NN43100-500) and version 2.2
of the firmware upgrade bulletin, it should be noted that the PDT login and password must be used instead of the
admin level 1 indicated.
To prevent overwriting previous release files, MPLR24008 must be loaded onto the MC32 cards before upgrading
from release 4.5 to 6.0+.
MC32 cards cannot be changed from leader to follower after upgrade. Confirm the Leader flag is not set before upgrade,
the 'itgCardShow' command should be executed in IPL shell on SMC card or OAM shell on MC32s card. If an output
contains "Role : Leader" string, the Leader flag is set. (Avaya Bulletin: PSN003377u )
FQDN
| Domain | If the Primary Security Server Domain is entered incorrectly, the element must be reinstalled from scratch.
| Hostname | If the host name is entered incorrectly, it can be changed via the networkconfig command
accessed while in Linux CLI.
UCM
| Patching | The Linux Base SU and SP patches MUST be loaded after completing the appinstall process but prior to
Performing the UCM Security Configuration. Failure to do so may cause database corruption.
Release 6 does not support Internet Explorer 7.0 and above.
Release 7 supports Internet Explorer 6.0, 7.0 and 8.0.
Other browser types and versions are not supported.
| Date/Time | If the date is not changed to the current date when installing a Linux server the certificates may fall.
| Security | A few sites have experienced the following behaviour:
| Config. | After completing the global security configuration process (when the new browser is opened and the UCM screen
appears) the Gobal Security configuration appears to have not yet been completed.
This is due to an error in the HOST or FQDN entry used. To resolve this check the HOST and FQDN configuration
in Linux to ensure it is correct.
| Certificate | Certain characters (listed below) cannot be used in the certificate descriptive fields (such as the organization field)
| Creation | Nortel recommends that only alpha/numeric characters be used.
Do not use a space or # sign as the first character
Do not use a space as the last character
Do not use a comma, plus sign, quote symbol, backslash, less than, greater than, or semi-colon
in any part of these fields.
| Logging In | When installing, upgrading or working with UCM framework (To get access to the UCM element List), it should be noted
that the FQDN of the UCM server MUST be used to log in. If the browser being used is connected to the LAN via a non-routed
ELAN subnet, the login attempts will fail, and the session may be directed to the base manager. Once Base Manager has
been installed it is best practice to use the TLAN subnet to configure and administer the UCM elements.
** To maintain a supported configuration, the TLAN subnet is routable to the CLAN subnet or at minimum to a subnet
where the IP Phones will reside. If the deployment is to be in an isolated network where the only devices on the
CLAN are the IP Phones, a DNS server must be deployed and configured as part of the CS1K installation and
located on the TLAN subnet.
System Manager
You must use FQDN to access EM via System Manager. IP is acceptable for System Manager and UCM, but not EM.
Meridian Mail
| Not | Meridian Mail is physically not supported under Release 5.x+
Supported
If the site to be upgraded currently has a Meridian Mail installed, it must be migrated or upgraded to a CallPilot
or other supported voice mail system prior to deploying the new CallServer software.
All hardware and software configurations relating to Meridian Mail must be removed from the CallServer prior to
upgrade. Once the upgrade has been completed, the ENET card configuration cannot be removed.
In the event the Meridian Mail is scheduled to be upgraded or migrated during the same timeframe as the CallServer
then an EDDY should be completed prior to removing the Meridian Mail configuration for blackout purposes.
An additional EDDY must be completed *without* the Meridian Mail configurations to be used during the
CallServer upgrade.
Network
| Layer 2 | ACL's (Access Control Lists) require MAC Addresses of new hardware (CP-PM, COTS) to be added or else you
can experience one-way speech issues.
FAX
Fax between MGC/X cabinets is a VOIP call. Special concideration is required for Fax over VOIP. See TAB on FAX for details.
MGxPEC
Gold Image on MGxPEC will fail loading FPGA. Install CSP LW first. ( Release 7.X)
6.00.18
In December 2009 the Linux Base Software for CS 1000 Release 6.0 systems was upgraded from 6.00.18 to 6.00.18.62 to
accommodate the deployment of IM and Presence functionality. At that time, all previous patches for 6.00.18.00 had been
integrated into the 6.00.18.62 base.
At this time, patch support for Linux Base Software 6.0.18.00 is being discontinued. For any future patching requirements,
the base software will need to be upgraded to 6.00.18.62 at a minimum.
Systems not requiring patch support at this time can remain on 6.00.18.00.
Systems requiring patch support will need to be upgraded to Linux Base Software version 6.00.18.62 prior to being patched.
Upgrade to 6.00.18.62 before logging any cases against older software releases.
MISC
The IBM 3350 COTS server requires a null cable, not the cable that came with the ISP-1100.
Option 11C
Automatic conversion is supported directly from an Option 11C.
The conversion will require an upgrade to a CPPM, CPDC processor and MGC, or CPMG - Not a CPPIV.
Option 61/81 and CS1000M SG & MG to CS1000E Database Conversions
An Option 61/81, CS1000M SG/MG database being migrated to a new CS1000E database requires modifications to the data to
create a new CS1000E database. However there is no supported software tool, or “In house conversion” (IHC) codes, to
provide the database conversion from an Option 61/81, CS1000M SG&MG to CS1000E
When considering an Option 61/81, CS1000M SG/MG to CS1000E migration quote or order, Avaya recommends including an item to
cover the cost of the CS1000E database conversion. This line item on the quote or order will cover the time needed to manually create
the new CS1000E database from the Option 61/81 or CS1000M SG/MG data
Do not use a DCH that starts with a 1 on a 1000e co-res
3900 sets upgrade prior to upgrade window
It is mandatory for all Communications Server 1000 customers upgrading to rls 6.0 to have their M3900 sets upgraded to the latest
firmware version prior to the core upgrade, failing to do so will cause problems with M3900 sets during Transfer call
scenarios, A fix for CR (Q01805423-01: 390x during a transfer call have no "Conf" softkey) was introduced, this fix
contains changes in both core and Taurus firmware, if Communications Server 1000 system is upgraded to rls 6.0 without upgrading M3900
sets then during the transfer scenario, after the second leg of the call is answered the connect key will not appear.
Customer's LAN based database

## Vintage Requirements
◄ Back to table of contents
Vintages
Release 5.5 and 6.0 have minimum vintage requirements for a number of cards and applications. This tab contains a list of
items that if present in the system must either be removed or updated to a minimum vintage as specified.
Note: This list may not represent an all inclusive list of cards and vintages. Be sure to reference the GRB document for the release
about to be installed to verify all requirements are met.
The General Release Bulletin (GRB) for the version of software to be installed should be read through to ensure all requirements are met.
In addition, Nortel document NN43001-140 Product Compatibility Matrix should be used to verify minimum vintages
and application interoperability levels.
Release 5.5
| Minimum Releases | Cards or applications with vintages not listed below must be replaced prior to or part of upgrade procedures.
|  | PEC | Description | Minimum Vintage |  | Notes
|  | NTRB53 | Clock Controller | AA and later
|  | NT5D12 | Dual port DTI/PRI | AC, AD, AG and AH
|  | NT5D11 | Line Side T1 | AE Release 3
|  | NT5D97 | DTI/PRI2 | AB and AD
|  | NTRB33 | FIJI Double Slot | AF (with version 21 Loadware)
|  | NTRB33 | FIJI Single Slot | BB (with version 29 Loadware)
|  | QPC441 | 3 Port Ext (3PE) | F
|  | QPC43 | PerSig | R |  | Bulletin 2007007688, Rev 2
|  | NT6D41 | DC Power Supp | CA
|  | NT8D29 | AC Power Supp | BA Rls 1 |  | Possible issues with Rls 3&4
|  | NT4N65 | CNI | AC
|  | NT4N48 | Utility Card | BA
|  | NT4N40 | Core/Net Shelf | AA or AB
|  | NT4N41 | Core/Net Module | AB AC DB DC
|  | NT4N39 | CP-PIV CPU | AA or AAE6
|  | NT8D41 | 4 Port SDI Paddle | BB
|  | NT6D80 | MSDL | AB or AC
|  | QPC471AH | Clock Controller | Allowed only on 61C
|  | NTDK20 | SSC CPU | HA JA
|  |  | Contact Center | Release 4.2
|  |  | Telephony Manager | Release 3.1 SU2
| No Longer Supported | The below cards and applications MUST be removed from the system prior to or part of upgrade procedures.
|  | PEC | Description | Replacement PEC | Description | Notes
|  | QPC139 | 2 port SDI | NT8D41BB | 4 Port Paddleboard
|  | QPC444 | Conference | NT8D17 | Conf/TDS
|  | QPC471 | Clock Controller | NTRB53 | Global Clock Ctrlr | QPC471 Supported for Opt 61
|  | QPC775 | Clock Controller | NTRB53 | Global Clock Ctrlr | QPC775 Supported for Opt 61
|  | QPC412 | IGS | Contact your Nortel Sales Engineer |  | Fiber Network Required
|  | NT5D30 | DIGS | Contact your Nortel Sales Engineer |  | Fiber Network Required
|  | QPC417 | Junctor Board IGM | Contact your Nortel Sales Engineer |  | Fiber Network Required
|  | NT6D65 | CNI | NT4N65C | cPCI CNI
|  | NTRB34 | CNI-3 | NT4N65C | cPCI CNI
|  | NT5D21 | Core/Net Module | NT4N41 | Core/Net Module
|  | NT5D61 | IODUC | Contact your Nortel Sales Engineer
|  | CNI Cables | CNI Cables | NT4N29AA | cCNI to 3PE Cable
|  | NT5D03 | CPU CP3 | NT4N39 | CP PIV
|  | NT5D10 | CPU CP4 | NT4N39 | CP PIV
|  | QPC472 | DTI | NT5D12 | Dual Port PRI
|  | QPC536 | DTI 2MB | NT5D97 | Dual Port PRI
|  | QPC720 | PRI/DTI | NT5D12 | Dual Port PRI
|  | QPC473 | DTI | NT5D97 | Dual Port PRI
|  | QPC786 | Digital Trunk and DB | Contact your Nortel Sales Engineer
|  | NT8D72 | PRI interface | Contact your Nortel Sales Engineer
|  | NTCK43 | PRI2 | NT5D97 | Dual Port PRI
|  | QPC757 | DCHI | NTBK57 | DCHI DB
|  | NT8D74 | Clock to IGM Cable | Contact your Nortel Sales Engineer |  | Fiber Network Required
|  | NT8D76 | IGS to IGM Cable | Contact your Nortel Sales Engineer |  | Fiber Network Required
|  | n/a | Companion Cards | Contact your Nortel Sales Engineer |  | WLAN Required
|  | n/a | IGM Terminators | Contact your Nortel Sales Engineer |  | Fiber Network Required
|  | n/a | Meridian Max | n/a | Contact Center 4.2
|  | n/a | Meridian Mail | n/a | CallPilot 5.0
|  | n/a | OTM | n/a | Telephony Manager 4.0
Release 6.0, 7.X
| Minimum Releases | Items listed above apply to Release 6.0 as well as the additional items list below.
Note: Items listed under 6.0 override any status under 5.x
|  | PEC | Description | Minimum Vintage |  | Notes
|  |  | Contact Center | Release 6.0
|  |  | CallPilot | Release 5.0
|  |  | Telephony Manager | Release 4.0
| No Longer Supported | The below cards and applications MUST be removed from the system prior to or part of upgrade procedures.
|  | PEC | Description | Replacement PEC | Description | Notes
|  | A0810496 | CP PII CPU | Contact your Nortel Sales Engineer
|  | NT4N43 | cPCI MMDU | Contact your Nortel Sales Engineer
|  | NT4N46 | cPCI Card Cage | Contact your Nortel Sales Engineer
|  | NT4N48 | cPCI Sys Util | Contact your Nortel Sales Engineer
|  | NTDK19 | SSC Upgrade Kit | Contact your Nortel Sales Engineer
|  | NTDK20 | SSC CPU | Contact your Nortel Sales Engineer
|  | NTDK50 | Main/Expansion Cabinet | Contact your Nortel Sales Engineer
|  | NTDU22 | Branch Office | Contact your Nortel Sales Engineer
|  | NTDU23 | Media Gateway Expansion | Contact your Nortel Sales Engineer
|  | NTDU24 | Media Gateway Trunks | Contact your Nortel Sales Engineer
|  | NTDU25 | Media Gateway Cable Kit | Contact your Nortel Sales Engineer
|  | NTDU27 | ISP1100 SS | Contact your Nortel Sales Engineer
Customer's LAN based database

## Upgrade Procedure R6
◄ Back to table of contents
Release 6.00R
If upgrading from any release and adding COTS Servers and/or new CP-PM's, these devices can have the
Linux base, Linux Base Patches, UCM Security Configuration done ahead of time, so that when going to
site it can be a seamless of the old ISP1000's and Processors.
Before performing an upgrade, create a backup of the database. Ensure that IPSEC/centralized authentication is disabled,
and leave the security domain before proceding to prevent connectivity and other malfunctions with UCM elements.
Back up database, then disable IPSEC/centralized authenthication (leave security domain),
otherwise this will cause issues including elements not able to join the UCM domain.
Installation Steps
Note: The following steps must be done to each CP PM or COTS server that will be installed.
| Linux Base Install | Notes:
| 1. Install Linux Base on a CP PM or COTS server | NN43001-315 - Linux Platform Fundamentals
| 2. Install Linux Base Patches | See product Bulletin from ESPL
| 3. Configure Security with UCM | NN43001-116 - UCM Security Configuration
4. Upload the nai file in order to deploy the applications.
| 5. Deploy Applications with Deployment Manager (SS, NRS, EM) | NN43001-315 - Linux Platform Fundamentals
| 6. Apply Service Pack | https://espl.avaya.com/espl/
To Restore old database to new platform
7. Convert old database with Database Utility Conversion Tool - this is to convert floppies to CF.
8. Put RMD in CP PM or CP IV
9. Restore Database
10. Reboot Call Server to active database.
To install new NRS Database.
1. Save NRS database from ISP1100 to desk top..NRSbackup.tar
2. Log into Primary Security Server
3. Select Elements, Primary NRS
Note: For other Flow Charts see NN43001-100

## Upgrade Procedure R7
◄ Back to table of contents
Release 7.00Q
If upgrading from any release and adding COTS Servers and/or new CP-PM's, these devices can have the Linux base,
Linux Base Patches, UCM Security Configuration done ahead of time, so that when going to site it can be a seamless
of the old ISP1000's and Processors.
Before performing an upgrade, create a backup of the database. Ensure that IPSEC/centralized authentication is disabled,
and leave the security domain before proceding to prevent connectivity and other malfunctions with UCM elements.
When upgrading Release 6.0 Servers. If they have the current Service Pack the upgrade can be pushed from the Deployment Server.
Installation Steps
Note: The following steps must be done to each CP PM or COTS server that will be installed.
| Linux Base Install Primary UCM | Notes:
| 1. Install Linux Base on a CP PM or COTS server | NN43001-315 - Linux Platform Fundamentals
| 2. Install Linux Base Patches | See product Bulletin from ESPL
| 3. Configure Security with UCM | NN43001-116 - UCM Security Configuration
| 4. Upload the nai file in order to deploy the applications. | NN43001-315 Linux Platform Base and Applications Installation and Commissioning
| 5 Create Deployment view | NN43001-315 Linux Platform Base and Applications Installation and Commissioning
| 6. Deploy Applications with Deployment Manager (SS, NRS, EM) | NN43001-315 Linux Platform Base and Applications Installation and Commissioning
| 7. Apply Service Pack | The SP is currently being posted as a zip file but MUST be renamed from .zip to .ntl once saved to your desktop
https://espl.avaya.com/espl/
Linux Base Install MEMBER
| 1. Install Linux Base on a CP PM or COTS server | NN43001-315 Linux Platform Base and Applications Installation and Commissioning
| 2. Install Linux Base Patches | See product Bulletin from ESPL
| 3. Configure Security with UCM | NN43001-116 - UCM Security Configuration
5 Create Deployment view on Primary UCM
| 6. Deploy Applications with Deployment Manager (SS, NRS, EM) | NN43001-315 - Linux Platform Fundamentals
To Restore old database to new platform
7. Convert old database with Database Utility Conversion Tool
8. Put RMD in CP PM or CP IV
9. Restore Database
10. Reboot Call Server to active database.
To install new NRS Database.
1. Save NRS database from ISP1100 to desk top..NRSbackup.tar
2. Log into Primary Security Server
3. Select Elements, Primary NRS
This information is subject to change - refer to the Product bulletin in ESPL
Linux SP Installation Instructions for New System Installations :
1. Upgrade the UCM primary security server to Release 7.0 software
2. Next, Install the latest ‘Linuxbase’ SU on the UCM Primary Security using CLI
a. upload nortel-cs1000-linuxbase-7.00.20.10-02.i386.000.ntl to /var/opt/nortel/patch.
b. pload nortel-cs1000-linuxbase-7.00.20.10-02.i386.000.ntl
c. pins <patch handle #>
3. Install the Baseweb SU on the UCM Primary Security Server using CLI method.
a. upload nortel- cs1000-baseWeb-7.00.20.10-00.i386.000.ntl to /var/opt/nortel/patch directory
b. pload nortel-cs1000-baseWeb-7.00.20.10-00.i386.000.ntl
c. pins <patch handle #>
4. Install the Patchweb SU on the UCM Primary Security Server using CLI method.
a. upload nortel-cs1000-patchWeb-7.00.20.10-01.i386.000.ntl to /var/opt/nortel/patch directory
b. pload nortel-cs1000-patchWeb-7.00.20.10-01.i386.000.ntl
c. pins <patch handle #>
5. Upload and install the SP on the UCM Primary Security (UCM Patch Manager can be used)
Note: SU’s/patches will only be applied if the Linux Applications are present. Applications should be deployed first.
If the Linux Base has been deployed only at installation or upgrade, then it will be required to reapply the SP after new applications are added.
6. Upgrade the member servers to Release 7.0 software using the Deployment Manager
7. Next deploy the Linuxbase SU to the Backup/Member Servers via CLI
8. Install the Baseweb and Patchweb SU’s to the Backup/Member Servers via UCM Patch Manager
9. Deploy the Service Pack to the Backup/Member Servers using UCM Patch Manager (Base Manager or CLI can also be used)

## Upgrade Procedure R 7.5
◄ Back to table of contents
Release 7.50Q/7.50.17
If upgrading from any release and adding COTS Servers and/or new CP-PM's, these devices can have the Linux base,
Linux Base Patches, UCM Security Configuration done ahead of time, so that when going to site it can be a seamless
of the old ISP1000's and Processors.
Before performing an upgrade, create a backup of the database. Ensure that IPSEC/centralized authentication is disabled,
and leave the security domain before proceding to prevent connectivity and other malfunctions with UCM elements.
When upgrading Release 6.0 and 7.0 the upgrade can be pushed from the Deployment Server.
Installation Steps
Note: The following steps must be done to each CP PM or COTS server that will be installed.
| Linux Base Install Primary UCM | Notes:
| 1. Install Linux Base on a CP PM or COTS server | NN43001-315 - Linux Platform Fundamentals
| 2. Install Linux Base Patches | See product Bulletin from ESPL
| 3. Configure Security with UCM | NN43001-116 - UCM Security Configuration
4. Upload the nai file in order to deploy the applications.
5 Create Deployment view
| 6. Deploy Applications with Deployment Manager (SS, NRS, EM) | NN43001-315 - Linux Platform Fundamentals
| 7. Apply Service Pack | The SP is currently being posted as a zip file but MUST be renamed from .zip to .ntl once saved to your desktop
https://espl.avaya.com/espl/
Linux Base Install MEMBER
| 1. Install Linux Base on a CP PM or COTS server | NN43001-315 - Linux Platform Fundamentals
| 2. Install Linux Base Patches | See product Bulletin from ESPL
| 3. Configure Security with UCM | NN43001-116 - UCM Security Configuration
5 Create Deployment view on Primary UCM
| 6. Deploy Applications with Deployment Manager (SS, NRS, EM) | NN43001-315 - Linux Platform Fundamentals
To Restore old database to new platform
7. Convert old database with Database Utility Conversion Tool
8. Put RMD in CP PM or CP IV
9. Restore Database
10. Reboot Call Server to active database.
To install new NRS Database.
1. Save NRS database from ISP1100 to desk top..NRSbackup.tar
2. Log into Primary Security Server
3. Select Elements, Primary NRS
Linux SP Installation Instructions for New System Installations :
1. Upgrade the UCM primary security server to Release 7.5 software
2. Next, Install the latest ‘Linuxbase’ SU on the UCM Primary Security using CLI
a. upload cs1000-linuxbase-7.50.17.xx-xx.i386.000.ntl to /var/opt/nortel/patch.
b. pload cs1000-linuxbase-7.50.17.xx-xx.i386.000.ntl
c. pins <patch handle #>
3. Install the Baseweb SU on the UCM Primary Security Server using CLI method.
a. upload cs1000-baseWeb-7.50.17.xx-xx.i386.000.ntl to /var/opt/nortel/patch directory
b. pload cs1000-baseWeb-7.50.17.xx-xx.i386.000.ntl
c. pins <patch handle #>
4. Upload and install the SP on the Primary Security server using Patch Manager
Note: SU’s/patches will only be applied if the Linux Applications are present.
Applications should be deployed first. If the Linux Base has been deployed only at
installation or upgrade, then it will be required to reapply the SP after new applications are added.
5. Upgrade the member servers to Release 7.5 software using the Deployment Manager
7. Install Linuxbase SU to the Backup/Member Servers using CLI
8. Deploy applications on members as needed.
9. Install Service Pack to the Backup/Member Servers using Patch Manager

## UCM Security issues
◄ Back to table of contents
UCM Security Issues
VxWorks Element request to join UCM
End User must confirm the confirm the fingerprint of the public key given to it from UCM
The VxWorks Element sends the password to UCM to authenticate
The VxWorks Element stores the UCM SSH key in /e/keys/xxx.xxx.xxx.xxx.properties
NFC API to sftp properties file to the UCM under directory: /var/opt/nortel/Jboss-Quantum/conf/elementRegistry/element/deployed
To view the content the files: cat <filename>
The registration process on UCM can be viewd in the server.log file /var/opt/nortel/Jboss-Quantum/log/server.log

## High Scalability
◄ Back to table of contents
High Scalability
NN43041-312 Communication Server 1000E High Scalability Installation and Commissioning

## Geographic Redundancy
◄ Back to table of contents
Geographic Redundancy
All components must belong to the same UCM domain.
Cores Callservers must have routes built to any elan device outside of their subnet.

## FAX issues with VOIP - MGC's
◄ Back to table of contents
Fax Issues with VOIP - MGC's
FAX Configuration Recommendations in the Call Server 1000
Fax settings and performance over VoIP solutions vary depending on the network configuration. In order
to achieve a successful faxing environment the VoIP solution has to be engineered properly. Following
are configuration and network design aspects that need to be taken into consideration when
implementing faxing in VoIP solutions:
CODECs:
T.38:
Older fax machines use V.21
For lower speeds (V.21) protocol T.38 should be used in the VoIP segments of the call. Modem Pass
Through (G.711): Newer fax machines use Modem Protocols to achieve higher speeds (V.34) The
Modem pass through feature is intended for modems and high speed faxes employing V.34, it uses clear
channel G.711 over the VoIP segments of the call.
The Modem Pass Through will detect the phase reversal tone negotiation used for higher speeds and
will tell the DSPs involved in the call to disable echo-cancellation and all other non linear components.
MPTD class of service for analog fax lines allows the change of the DSPs between T.38 for lower speeds
and G711 for higher speeds.
VERY IMPORTANT
MPTD must be used on ALC (Analog Line Cards) units connected to Fax machines when there are trunk
cards present in same and other IPMGs that connect to PSTN. This is required to support T.38 and V.34
faxes that could originate or terminate from/to the PSTN.
In order for MPTD to work a system bandwidth strategy of BQ (Best Quality) must be used.
The CLS MPTA should be used only for Modems, it will force all calls to use G711.When going to the
PSTN we have no control over the far end, however if the far end supports T.38 and Modem Pass
Through, speeds of 33.6 should be achievable.
ATTENTION
Fax performance at higher speeds (33.6) requires that all network elements are properly engineered to
support it. When high speed faxes cannot be achieved with a consistent success rate it is recommended
to set the fax units at a lower speed (14.4).
Scenarios:
Typical scenarios for Faxing in a CS1KE solution:
a) Two faxes connected to analog lines in the same MGC (TDM call, no DSPs)
b) Two faxes connected to analog lines in different MGCs of the same CS1K (DSPs are used)
c) One fax connected to analog line in an MGC to IP Trunk to a remote system with a fax
d) One fax connected to analog line in an MGC to Analog trunk in same MGC to PSTN (Local or LD) fax
(No DSPs are involved)
e) One fax connected to analog line in an MGC to Digital trunk in same MGC to PSTN (Local or LD) fax
(No DSPs are involved)
f) One fax connected to analog line in an MGC to Digital trunk in different MGC of the same CS1KE to
PSTN (Local and LD) fax (DSPs are used)
Note: The following scenario is not fully supported for faxing:
One fax connected to analog line in an MGC to Analog trunk in different MGC of the same CS1KE to PSTN (Local or LD) fax
Data Network:
Depending on the fax scenarios fax calls can traverse the IP network, either internally (ex: MGC to MGC)
or externally (ex: IP Trunks). It is important to engineer the data network to support the following:
Media card configuration:
G.711/T.38 codecs
20 ms packet size
Round trip delay must be less than 50 ms
Packet loss must be less than 0.5%
V.34 rate (33.6 kbit/s) as long as far end supports Modem Pass Through feature
Mean Jitter is less than 5 ms
ATTENTION
Performance degrades significantly with packet loss (must be less than 0.5%) and when the delay (round
trip) is greater than 50 msec and mean jitter is greater than 5msec.
ATTENTION
Avaya has conducted extensive but not exhaustive tests of fax calls in different scenarios. While all tests
have been successful, Avaya cannot guarantee that all fax brands will operate properly over all G.711
Voice over IP (VoIP) networks. Before you deploy faxes, test the fax within the network to verify reliable
operation. Contact your system supplier or your Avaya representative for more information.
Call Server
Typical recommended configuration for analog lines cards connected to faxes:
MGCs:
Enable modem/fax pass through mode: Should be enabled in element manager
Enable V.21 FAX tone detection: Should be enabled in element manager
VGW trunks should be in a zone with Best Quality (BQ) setting.
Analog Lines:
Class of service: FAXA, this will set the proper trunk capability for fax calls.
Class of service: MPTD, this setting will allow lower speed faxes (up to 14.4) to use T.38 and higher
speed faxes to use G711 clear channel (no echo cancelation, no nonlinear DSP features).

## Post check
◄ Back to table of contents
Post check
Meets specifications:
1. All cores are in service and redundant (use switchovers to verify).
2. All NRS are redundant.
3. All Signaling Servers, MGCs, IPMGs, MC32S, NRS, and so on are in service.
4. Patching, Loadware, and firmware levels for all nodes and cards (such as Cores,
Signaling Servers, NRS, and so on) are up to date.
If the latest Deplist/SUs are not applied, highlight and document the reason.
5. All elements are upgraded to the latest software release.
6. Review the alarms for the following:
o Both Cores
o Lead and one Follower Signaling Server
o 2 MC32 cards (if present)
o 2 MC32S cards (if present)
o 2 IPMGs (if present) (*Any unexpected restarts need to be documented.)
o Primary NRS
*Document any BERR0705 or unexpected restarts in an SR for follow-up investigation.
7. All trunk groups that were in service before the upgrade need to be verified to be in service
after the upgrade.
8. All phones are registered.
9. Load balancing is in place and working on the Signaling Servers.
10. Validate all registered elements:
o Select UCM Secure FTP token link and regenerate the tokens.
o Elements with issues will fail to receive the token.
11. All FIJI cards and rings verified to be in service (customer to verify and report back).
12. All fax machines can receive and send calls/faxes (customer to verify and report back).
13. All critical call models have been verified to completed (customer to verify and report back).
14. All fax machines are SIP compliant.